## ProjectSchedule
Project B.A.T. (Blueprint Automation Tool)
Enter Company Name in cell B2. | COMP 195- Senior Project
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Kevin Green | Project Start: |  | 2022-01-19
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-01-17 to 2022-03-13
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-01-17 to 2022-03-13
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
| Project Proposal Creation |  | 100% | 2022-01-19 | 2022-01-26
| Project Proposal |  | 100% | 2022-01-26 | 2022-01-26
| System Design Document Creation |  | 100% | 2022-01-27 | 2022-02-06
| Cover Page | Kevin | 100% | 2022-01-27 | 2022-01-27
| System Architecture | Kevin | 100% | 2022-01-27 | 2022-01-28
| Hardware, Software, and System Requirements | Kevin | 100% | 2022-01-31 | 2022-02-01
| External Interfaces | Kevin | 100% | 2022-01-29 | 2022-01-30
| Software Design | Kevin | 100% | 2022-02-02 | 2022-02-03
| User Interface Design | Kevin | 100% | 2022-02-04 | 2022-02-05
| Glossary of Terms | Kevin | 100% | 2022-02-06 | 2022-02-06
| References | Kevin | 100% | 2022-02-06 | 2022-02-06
| System Design Document |  | 100% | 2022-02-06 | 2022-02-06
| Project Planning |  | 100% | 2022-02-07 | 2022-02-11
| Project Steps Creation | Kevin | 100% | 2022-02-07 | 2022-02-09
| Gantt Chart Creation | Kevin | 100% | 2022-02-10 | 2022-02-11
| Window Automation Implementation |  | 80% | 2022-02-07 | 2022-02-17
| Getting All Open Windows | Kevin | 100% | 2022-02-07 | 2022-02-07
| Finding Window | Kevin | 100% | 2022-02-08 | 2022-02-10
| Bring Window To Foreground | Kevin | 100% | 2022-02-11 | 2022-02-12
| Moving/Resizing Window | Kevin | 100% | 2022-02-13 | 2022-02-15
| Implementation Testing | Kevin | 75% | 2022-02-16 | 2022-02-17
| Keyboard Automation Implementation |  |  | 2022-02-18 | 2022-02-27
| Pressing and Releasing "Virtual Keys" | Kevin |  | 2022-02-18 | 2022-02-20
| Parsing strings into list of VK Hex Codes | Kevin |  | 2022-02-21 | 2022-02-23
| Copy/Paste Mechanics | Kevin |  | 2022-02-24 | 2022-02-25
| Implementation Testing | Kevin |  | 2022-02-26 | 2022-02-27
| Project Snapshot 1 |  |  | 2022-02-27 | 2022-02-27
| Game Automation |  |  | 2022-02-21 | 2022-03-13
| Detection of Game Version | Kevin |  | 2022-02-21 | 2022-02-27
| Execution of In-Game Commands | Kevin |  | 2022-02-28 | 2022-03-04
| Teleportation Through World | Kevin |  | 2022-03-05 | 2022-03-07
| Executing WorldEdit Commands | Kevin |  | 2022-03-08 | 2022-03-11
| Implementation Testing | Kevin |  | 2022-03-12 | 2022-03-14
| "Places" Parsing |  |  | 2022-03-14 | 2022-03-20
| Reading Lines | Kevin |  | 2022-03-14 | 2022-03-14
| Reading Polygons | Kevin |  | 2022-03-15 | 2022-03-15
| Reading Circles | Kevin |  | 2022-03-16 | 2022-03-16
| Reading Paths | Kevin |  | 2022-03-17 | 2022-03-17
| Converting Geo-Coords to Minecraft | Kevin |  | 2022-03-18 | 2022-03-18
| Implementation Testing | Kevin |  | 2022-03-19 | 2022-03-20
| Project Snapshot 2 |  |  | 2022-03-20 | 2022-03-20
| Integrate Parsing into Game Automation |  |  | 2022-03-21 | 2022-03-27
| Passing Coordinates to the Game Automator | Kevin |  | 2022-03-21 | 2022-03-23
| Drawing Lines Based on Map Projection | Kevin |  | 2022-03-24 | 2022-03-27
| Saving/Loading Settings Implementation |  |  | 2022-03-28 | 2022-04-03
| Default Block Height | Kevin |  | 2022-03-28 | 2022-03-28
| Block Choice | Kevin |  | 2022-03-29 | 2022-03-29
| Scaling Factor | Kevin |  | 2022-03-30 | 2022-03-31
| Reference Coordinate | Kevin |  | 2022-04-01 | 2022-04-01
| Implementation Testing | Kevin |  | 2022-04-02 | 2022-04-03
| Project Snapshot 3 |  |  | 2022-04-03 | 2022-04-03
| User Interface Implementation |  |  | 2022-04-04 | 2022-04-17
| Create Home Screen | Kevin |  | 2022-04-04 | 2022-04-10
| Configuration Screen | Kevin |  | 2022-04-11 | 2022-04-17
| Project Snapshot 4 |  |  | 2022-04-17 | 2022-04-17
| Debugging, Testing |  |  | 2022-04-18 | 2022-05-01
| Creation of Test Cases | Kevin |  | 2022-04-18 | 2022-04-21
| Normal Use Case Testing | Kevin |  | 2022-04-22 | 2022-04-24
| Edge Case Testing | Kevin |  | 2022-04-25 | 2022-04-28
| User Testing | Kevin |  | 2022-04-29 | 2022-05-01
| Final Project Implementation |  |  | 2022-05-04 | 2022-05-04
| Senior Project Day Preparation |  |  | 2022-05-02 | 2022-05-06
| Final Documentation Updates | Kevin |  | 2022-05-02 | 2022-05-03
| Poster Creation | Kevin |  | 2022-05-04 | 2022-05-06
| Oral Presentation Preparation | Kevin |  | 2022-05-04 | 2022-05-06
| Senior Project Poster |  |  | 2022-05-06 | 2022-05-06
| Senior Project Day Oral Presentation |  |  | 2022-05-07 | 2022-05-07
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.